## Tasks
S.No	Tasks	Status	JM	KS
1	Find a way to read the Unique ID for every mote and store in a table for every mote	Done		♥
2	Sensor – Temperature	Done		♥
3	Sensor - Servo	Done		♥
4	Sensor – Light	Done	♥		Needs Testing
5	Sensor – Wind	Done	♥
6	Sensor – Joystick	Done	♥
7	Packet definition	Done
8	Get absolute time from BS/Gateway		♥
9	Maintenance Node Function
10	Maintenance Node Logic
11	GUI Design	Done	♥
12	implement UART	Done	♥
13	implement Network graph	Done	♥
14	Implement Sensor values		♥
15	Talk about routing protocol	Done
16	open broadcast after startup	Done
17	exchange distance vector with neighbors	Done
18	complete own distance vector with aid of xneighbor vectors	Done
19	Add different packet types MANUAL, PATH, ACK,UNI, EMERGENCY, DISC	Done	♥	♥
20	Change ACKMODE to PATHMODE	Done	♥	♥
21	Complete the Unicast function		♥	♥
22	Set a time out for broadcast receive inactivity	Done	♥	♥
23	Get ACK and the HOP Route of a mote	Done	♥	♥
24	Set up the ACK mode packet and send	Done	♥	♥
25	Add a delay between broadcasts	Done		♥
26	Add RIME ID and Mote Net ID at reset	Done
27	Add emergency function			♥
28	Documentation	Done	♥	♥
29	Doxygen		♥	♥
30	Presentation		♥	♥

## Optimisations
S.No	Description
1	Constant lookup times for routing table searches using hashes
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20